Project Omega (2026) – Fictional Migration Budget (Labor & Effort)

On-Prem to Azure Migration of 188 Applications • Hours & Roles • Azure Consumption Costs TBD

Budget Overview

This fictional budget estimate is designed for Microsoft Copilot training demonstrations. It includes project labor hours and effort by role for a one-year (2026) program to migrate 188 on‑premises applications to Azure using a migration factory model. Azure subscription/consumption costs are called out as a separate TBD category.

Team Model (Reasonable Program Team Size)

Project Omega is staffed as a mid-sized migration program with leadership, governance, and delivery teams.

| Role / Function | FTE Count | Notes |
| --- | --- | --- |
| Executive Sponsor (Business) | 0.1 | Steering and approvals |
| Program Manager | 1 | Overall delivery, reporting, risk management |
| Project Manager / Scrum Master | 1 | Wave execution, sprint facilitation |
| Cloud Solution Architect (Lead) | 1 | Target architecture, patterns, standards |
| Azure Platform Engineer | 2 | Landing zone, networking, identity integration |
| Security Engineer | 1 | Policies, guardrails, reviews, vulnerability management |
| DevOps Engineer | 2 | CI/CD templates, automation, IaC pipelines |
| Application Migration Engineers | 6 | Rehost/refactor execution, remediation |
| Database Engineer | 1 | Data migration planning, DB modernization support |
| QA / Test Lead | 1 | Test strategy, validation gates |
| QA/Test Analysts | 2 | Regression, smoke, and performance test execution |
| Change Management Lead | 1 | Communications, training, stakeholder readiness |
| Business Analysts (App Owners Liaison) | 2 | Requirements, acceptance criteria, UAT coordination |
| Operations / SRE Representative | 1 | Support model readiness, monitoring, runbooks |

Labor Hours Assumptions (Fictional)

2026 project duration: 12 months

Standard work month: ~160 hours per FTE

Some leadership roles are fractional (e.g., Executive Sponsor at 10%)

Migration factory model: execution throughput increases after Wave 1 pilot

Includes time for governance, planning, testing, stabilization, and closeout activities

Estimated Hours by Role (Labor Only)

| Role | FTE | Months | Hours/Month | Total Hours (2026) |
| --- | --- | --- | --- | --- |
| Executive Sponsor (0.1 FTE) | 0.1 | 12 | 160 | 192 |
| Program Manager (1 FTE) | 1 | 12 | 160 | 1920 |
| Project Manager/Scrum Master (1 FTE) | 1 | 12 | 160 | 1920 |
| Cloud Solution Architect (1 FTE) | 1 | 12 | 160 | 1920 |
| Azure Platform Engineers (2 FTE) | 2 | 12 | 160 | 3840 |
| Security Engineer (1 FTE) | 1 | 12 | 160 | 1920 |
| DevOps Engineers (2 FTE) | 2 | 12 | 160 | 3840 |
| App Migration Engineers (6 FTE) | 6 | 12 | 160 | 11520 |
| Database Engineer (1 FTE) | 1 | 12 | 160 | 1920 |
| QA/Test Lead (1 FTE) | 1 | 12 | 160 | 1920 |
| QA/Test Analysts (2 FTE) | 2 | 12 | 160 | 3840 |
| Change Management Lead (1 FTE) | 1 | 12 | 160 | 1920 |
| Business Analysts (2 FTE) | 2 | 12 | 160 | 3840 |
| Ops/SRE Representative (1 FTE) | 1 | 12 | 160 | 1920 |
| TOTAL (Labor Hours) |  |  |  | 42432 |

Effort Allocation by Phase (Fictional)

| Phase | Estimated Share of Labor |
| --- | --- |
| Initiation & Governance Setup (Jan) | 8% |
| Discovery & Assessment (Jan–Feb) | 12% |
| Azure Foundation / Landing Zone (Feb–Mar) | 10% |
| Detailed Planning & Wave Design (Mar) | 6% |
| Migration Execution (Apr–Oct) | 45% |
| Testing & Stabilization (May–Nov) | 14% |
| Closeout & Transition (Dec) | 5% |

Additional Budget Categories (Not Included in Labor Hours)

Azure subscription / consumption charges (Compute, Storage, Networking, PaaS services) — TBD

Third-party tools/licenses (e.g., migration tooling, security scanning) — TBD

Training & enablement (Azure workshops, security training) — TBD

Contingency reserve for high-risk applications — recommended 10–15% of labor

Optional Line Items to Make the Demo Feel Real

Travel / workshops (if distributed teams): limited on-site cutover support

Extended support coverage during critical cutovers (Waves 5–6)

Performance testing environment costs (non-production)

External consulting surge capacity for peak migration months

Disclaimer

This document is fictional and provided for training/demo purposes only. It is not an official project plan, estimate, or statement of work.