Project Omega (2026) – Fictional Migration Timeline

On-Prem to Azure Migration of 188 Applications • Generated January 21, 2026

Project Summary

Project Omega is a fictional 2026 modernization initiative designed for training demos. The goal is to migrate 188 on‑premises applications to Microsoft Azure using a phased approach that includes discovery, planning, execution, testing, governance, and closeout.

Scope & Assumptions (Fictional)

Total applications: 188 (mix of web apps, APIs, batch jobs, and vendor-packaged solutions)

Migration approach: Wave-based (6 waves), using Rehost/Refactor/Retire/Replace strategies

Target cloud platform: Microsoft Azure (landing zone + shared services)

Applications will be prioritized by business criticality and technical complexity

Parallel workstreams: platform foundation, security/governance, migration factory, QA/testing, and change management

High-Level Timeline (2026)

| Phase | Month(s) | Primary Outcomes |
| --- | --- | --- |
| 1. Initiation & Governance Setup | Jan | Project kickoff, leadership alignment, governance and reporting established |
| 2. Discovery & Assessment | Jan–Feb | App inventory validated, dependency mapping, migration strategy per app |
| 3. Azure Foundation (Landing Zone) | Feb–Mar | Networking, identity, security baseline, logging/monitoring |
| 4. Detailed Planning & Wave Design | Mar | Wave plan, runbooks, cutover patterns, test strategy |
| 5. Migration Execution (Waves 1–6) | Apr–Oct | Apps migrated in controlled waves with continuous improvements |
| 6. Testing, Stabilization & Hardening | May–Nov | Performance tuning, resiliency, security validation, UAT support |
| 7. Decommissioning & Optimization | Sep–Nov | Legacy shutdowns, cost optimization, documentation finalization |
| 8. Closeout & Transition to Operations | Dec | Final reporting, lessons learned, handoff to support teams |

Wave Plan (Fictional)

Applications are migrated in 6 execution waves. Wave capacity increases as the migration factory matures.

| Wave | Timing | Target App Count | Typical Complexity Profile | Notes |
| --- | --- | --- | --- | --- |
| Wave 1 | Apr | 18 | Low | Pilot wave; focus on repeatable runbooks and patterns |
| Wave 2 | May | 28 | Low–Medium | Scaled execution; introduce CI/CD and infra templates |
| Wave 3 | Jun–Jul | 36 | Medium | Increase throughput; more data/service dependencies |
| Wave 4 | Aug | 36 | Medium | Parallel cutovers; expanded UAT coordination |
| Wave 5 | Sep | 35 | Medium–High | Harder workloads; special change windows |
| Wave 6 | Oct | 35 | High | Business-critical systems; extended stabilization |

Key Workstreams & Activities by Phase

1) Planning & Readiness (Jan–Mar)

Executive sponsor alignment and program charter

Project governance: steering committee, change control, architecture review board (ARB)

Application inventory validation, dependency discovery, and environment mapping

Azure landing zone buildout (subscription strategy, networking, identity, policy)

Migration patterns and templates (IaC, pipelines, monitoring, tagging standards)

Security baselines: RBAC model, key vault standards, logging/alerting, vulnerability scanning approach

Test strategy: unit/regression/UAT performance and rollback criteria

2) Execution (Apr–Oct)

Migration factory operations (repeatable intake → build → migrate → validate workflow)

Wave-based cutovers with defined “go/no-go” checkpoints

Data migration events aligned with cutover windows (where applicable)

Continuous improvement (runbooks, automation, velocity tuning)

Weekly leadership reporting and risk management

3) Testing & Stabilization (May–Nov)

Functional validation and smoke testing after each migration

Performance testing for targeted apps (especially Waves 5–6)

Security validation (pen tests, configuration checks, policy compliance)

UAT coordination with business owners and service desk readiness

Stabilization period after each wave (bug fixes, tuning, monitoring improvements)

4) Governance & Compliance (Jan–Dec, ongoing)

Architecture and security reviews for new patterns and major refactors

Policy enforcement (resource tagging, network rules, approved services)

Cost governance: FinOps reporting and budget guardrails

Release/change management aligned to corporate CAB processes

Monthly steering committee readout and KPI tracking

5) Closeout (Dec)

Final migration validation and stabilization sign-off

Legacy decommission confirmation and asset inventory updates

Final documentation: runbooks, architecture diagrams, support SOPs

Lessons learned workshop and recommended roadmap for 2027 modernization

Transition to steady-state operations (SRE/Platform/Support)

Key Milestones (Fictional)

| Milestone | Target Date | Definition of Done (DoD) |
| --- | --- | --- |
| Project Kickoff Complete | Jan 15, 2026 | Charter approved; roles assigned; governance cadence established |
| Discovery Complete | Feb 28, 2026 | 188 apps categorized; dependencies documented; migration strategy assigned |
| Landing Zone Ready | Mar 15, 2026 | Networking, identity, policy, logging/monitoring operational |
| Wave 1 Complete | Apr 30, 2026 | Pilot apps migrated; runbooks validated |
| Wave 3 Complete | Jul 31, 2026 | Factory velocity stable; 80+ apps migrated |
| Wave 6 Complete | Oct 31, 2026 | All 188 apps migrated; cutover success criteria met |
| Decommissioning Complete | Nov 30, 2026 | Legacy environments shutdown/archived; CMDB updated |
| Project Closeout | Dec 15, 2026 | Final report delivered; support handoff complete |

Disclaimer

This document is fictional and provided for training/demo purposes only. It is not an official project plan, estimate, or statement of work.